## Product Backlog
Order | Task | Who | Size | Status | Delivered
10 | Write up user stories | Brent & Cece & Danial & Ehsun | 3 | Done | 3
20 | Product backlog | Danial | 1 | Started
30 | Risk log | Anthony, Chengzong, Danial | 3 | Done | 3
40 | Role allocation | All | 1 | Done | 1
50 | Glossary | Danial, Ehsun | 3 | Done | 3
60 | Class Diagram | All | 5 | Done | 5
70 | Meeting minutes | Brent | 1 | Started
80 | Requirements questions | All | 3 | Done | 3
90 | Definition of Done | Danial | 1 | Done | 1
100 | Proof Reading of Documentation | Brent & Ehsun | 1 | Done | 1
110 | Uploading project skeleton | Ehsun & Danial | 1 | Done | 1
120 | Setting up Travis File | Akio & Ehsun | 2 | Done | 2
130 | Architectural design---- | All | 5 | Done | 5
140 | Software class design | Brent, Ehsun & Danial | 3 | Done | 3
150 | Do research to prepare for UI development | Akio & Cece | 1 | Done | 1
160 | UI Mock-ups | Akio & Cece | 5 | Done | 5
170 | Sprint retrospective | All | 1 | Done | 1
180 | Update risk log | Danial | 1 | Done | 1
188 | Testing of features manually | Anthony, Chengzong | 3 | Done | 3
189 | Automated testing of features | Danial, Ehsun | 5 | Done | 5
190 | Gherkin feature files | Chengzong, Chak, Anthony, Danial, Ehsun | 5 | Done | 5
200 | Learner can register an account (M) | Danial, Ehsun | 1 | Done | 1
210 | Lecturer can register an account (M) | Danial, Ehsun | 1 | Done | 1
220 | Administrator can register an admin account (M) | Danial, Ehsun | 1 | Done | 1
230 | Learner can reset password (M) | Danial, Ehsun | 3 | Done | 3
240 | Lecturer can reset password (M) | Danial, Ehsun | 3 | Done | 3
250 | Administrator can reset password (M) | Danial, Ehsun | 3 | Done | 3
260 | Lecturer can upload videos (M) | Danial | 2 | Done | 2
270 | Lecturer can upload slide-show presentations (M) | Danial | 2 | -
280 | Lecturer can upload photos (M) | Danial | 2 | Done | 2
290 | Lecturer can upload documents (M) | Danial | 2 | Done | 2
291 | Learner will be emailed a code upon attempting to login | Danial,Ehsun | 3 | Done | 3
292 | Lecturer will be emailed a code upon attempting to login | Danial,Ehsun | 1 | Done | 1
293 | Admin will be emailed a code upon attempting to login | Danial,Ehsun | 1 | Done | 1
300 | Learner can enrol on a course (M) | Danial | 1 | Done | 1
310 | Learner can access free courses (M) | Danial | 3 | Done | 3
320 | Learner can leave feedback on reviews of courses (M) | Danial | 5 | Done | 5
330 | Learner can review a course after 50% completion (M) | Danial, Ehsun | 3 | Done | 3
340 | Administrator can monitor content (M) | Danial, Ehsun | 8 | Done | 8
350 | Administrator can view reports about learners (M) | Danial, Ehsun | 8 | Done | 8
360 | Administrator can view reports about lecturers (M) | Danial, Ehsun | 8 | Done | 8
370 | Administrator can delete account after 15 months of inactivity (M) | Danial, Ehsun | 8 | Done | 8
380 | Administrator can suspend an account for a period of time (M) | Danial, Ehsun | 8 | Done | 8
390 | Lecturer can submit a meet-up location form (M) | Ehsun, Danial | 2 | Done | 2
400 | Learner can view meet-up location on a map (M) | Ehsun | 5 | Done | 5
401 | Learner can edit profile information (M) | Danial | 2 | Done | 2
402 | Lecturer can edit profile information (M) | Danial | 2 | Done | 2
410 | Learner can use directions on the map (O) | Ehsun | 5 | Done | 5
420 | Learner can find public libraries using maps (O) |  | 5
430 | Learner can take assessments (O) |  | 3
440 | Lecturer can upload feedback and marks for the learner (O) |  | 3
450 | Learner can view feedback of assessments (O) |  | 3
460 | Lecturer can award performance badges (0) |  | 2
470 | Learner can gain performance badges (O) |  | 3 | -
480 | Learner can view performance badges on profile (O) |  | 2 | -
490 | Learner can sign up to notifications of enrolled courses (O) |  | 2 | -
500 | Learner receives notifications of enrolled courses (O) | Danial, Ehsun | 5 | Done | 5
510 | Learner can sign up to new course notifications (O) |  | 2
520 | Learner receives new course notifications (O) | Ehsun, Danial | 5 | Done | 5
530 | Learner can sign up to live news feeds (O) |  | 5
540 | Learner can view live news feeds (O) |  | 3
550 | Live chat feature for lecturers (O) |  | 13
560 | Live chat feature for learners (O) |  | 13
570 | Learner can change colour scheme to grey-scale (O) | Danial | 3 | Done | 3
580 | Learner can change font size (O) |  | 2
590 | Learner can search books in e-library (O) |  | 5
600 | Lecturer sets prices of courses (A) | Danial, Ehsun | 2 | Done | 2
690 | Lecturer can inform learners about events (A) | Danial, Ehsun | 2 | Done | 2
710 | Administrator can verify lecturer account (A) | Danial, Ehsun | 5 | Done | 5

## Analytics
|  | Date | Planned | Completed
Delivered | 165 | 2017-01-25 | 20 | 0
Planned | 235 | 2017-01-26 | 20 | 0 |  | Data
|  | 2017-01-31 | 20 | 9 | Who | Sum - Size | Sum - Delivered
|  | 2017-02-03 | 20 | 10 | Akio & Cece | 6
|  | 2017-02-07 | 253 | 19 | Akio & Ehsun | 2 | 2
|  | 2017-02-08 | 253 | 21 | All | 248 | 9
|  | 2017-02-13 | 254 | 21 | Anthony, Chengzong, Danial | 3 | 3
|  | 2017-02-14 | 273 | 22 | Brent | 1
|  | 2017-02-21 | 273 | 23 | Brent & Cece & Danial & Ehsun | 3 | 3
|  | 2017-04-15 | 286 | 51 | Brent & Ehsun | 1 | 1
|  | 2017-04-22 | 286 | 76 | Brent, Ehsun & Danial | 3
|  | 2017-04-29 | 282 | 128 | Chengzong, Chak, Anthony | 5
|  | 2017-04-30 | 235 | 165 | Danial | 2 | 1
[5 empty] | Danial, Ehsun | 3 | 3
[5 empty] | Ehsun & Danial | 1 | 1
(empty)
[5 empty] | Total Result | 278 | 23